## Title
Name of Work | Road Construction and Maintenance at Govt. Hospital Complex, Tonk
Agency | M/s. Rajesh Constructions Jaipur
Date of Bill | 2025-10-15
Tender Premium | 4.5
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
WORK ORDER
Cash Book Voucher No. |  | Date-
Name of Contractor or supplier : |  | M/s. Rajesh Constructions Jaipur
Name of Work ;- |  | Road Construction and Maintenance at Govt. Hospital Complex, Tonk
Serial No. of this bill : |  | Running Bill No. 1

## Bill Quantity
Item No | Description | Unit | Qty | Rate | Amount | Prev Qty
1.0 | Earthwork in excavation in ordinary soil including disposal of surplus earth, watering, ramming, levelling, cleaning etc. complete as per specification chapter C-01 & C-02 and as per drawing no. 1234/CW/01 dated 15.05.2024. For additional technical parameters of work refer Annexure 'A' attached with this BSR | Cum | 0 | 0 | 0 | 0
2 | Excavation upto 1.5 m depth | Cum | 28.71 | 450 | 12919.5 | 0
3 | Excavation upto 3.0 m depth | Cum | 35.28 | 520 | 18345.6 | 0
2.0 | Providing and laying PCC 1:3:6 using 40 mm down hand broken stone ballast, coarse sand conforming to IS: 2116 and OPC 53 grade conforming to IS: 8112 including mixing, laying, levelling, compacting, curing etc. complete as per specification chapter C-03. For additional technical parameters of work refer Annexure 'A' attached with this BSR |  | 0 | 0 | 0 | 0
5 | PCC in foundation | Cum | 47.89 | 3200 | 153248 | 0
3.0 | RCC M20 using 20 mm down hand broken stone ballast, coarse sand conforming to IS: 2116, OPC 53 grade conforming to IS: 8112 and processed water including mixing, pouring, vibrating, levelling, finishing, curing etc. complete as per specification chapter C-04. For additional technical parameters of work refer Annexure 'A' attached with this BSR |  | 0 | 0 | 0 | 0
7 | RCC in slab | Cum | 46.89 | 6800 | 318852 | 0
8 | RCC in beam | Cum | 12.5 | 7200 | 90000 | 0
4.0 | Brickwork in cement mortar 1:6 using standard size bricks conforming to IS: 1077 and coarse sand conforming to IS: 2116 including curing etc. complete as per specification chapter B-01. For additional technical parameters of work refer Annexure 'A' attached with this BSR |  | 0 | 0 | 0 | 0
10 | Brickwork in superstructure | Cum | 32.77 | 4800 | 157296 | 0

## Extra Items
Item No | Description | Unit | Qty | Rate | Amount | Prev Qty
E1 | Additional excavation due to unexpected rock layer | Cum | 15.36 | 650 | 9984 | 0
E2 | Extra RCC work for additional column | Cum | 9.6 | 7500 | 72000 | 0
E3 | Additional waterproofing treatment | Sq.m | 8.67 | 85 | 736.95 | 0

## Work Order
WORK ORDER
This is to certify that the work mentioned above has been executed as per the terms and conditions of the contract.
Engineer In Charge | Contractor
_________________ | _________________